## Team
Initials | First | Last | Email | GitHub Username | Roles
st | Sonali | Thaker | sthaker@stevens.edu | 1992sthaker | Design
dp | Dhruvil | Parikh | dparikh@stevens.edu | parikhdhruvil007 | Development
ss | Sarvesh | Shah | sshah73@stevens.edu | sshah73 | Design/Production
ak | Abdullah | Khanfor | akhanfor@stevens.edu | akhanfor | Design
ns | Nikhil | Seshagiri | nseshagi@stevens.edu | NikhilNS | Production/Pricing
kp | Kajal | Patel | kpate46@stevens.edu | Kajal396 | Design
dp1 | Drasty | Patel | dpate61@stevens.edu | DrashtiSSW | Development/Database
np | Neel | Patel | npate32@stevens.edu | Neelmufc | Development/Database
|  |  | GitHub Repository: | Hoboken LMS

## Sprint backlog
| Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed | Added
1 | US01 | Site Skeleton | dp,st,dp,ss,kp,np,ns,ak | complete | 50 | 120 | 30 | 60 | 2015-04-04 | 2015-04-16
1 | US02 | Home Page | dp,dp,np | complete | 30 | 120 | 40 | 30 | 2015-04-10 | 2015-04-16
1 | US03 | Log In Pane/Log out | dp,np | complete | 30 | 60 | 40 | 30 | 2015-04-11 | 2015-04-16
1 | US04 | Registration Page | dp,dp,np | complete | 40 | 90 | 30 | 50 | 2015-04-11 | 2015-04-16
2 | US05 | About Us Page | dp,st,ns | complete | 30 | 60 | 40 | 40 | 2015-04-16 | 2015-04-16
2 | US06 | Website Design (Uniform) | st,ss,kp,ak | complete | 60 | 240 | 70 | 90 | 2015-04-16 | 2015-04-16
2 | US07 | Contact Us (Feedback) Page | st,dp,ns | complete | 80 | 60 | 50 | 20 | 2015-04-16 | 2015-04-16
2 | US08 | FAQs page | dp,ns | complete | 50 | 90 | 70 | 60 | 2015-04-20 | 2015-04-25
2 | US09 | Status Page | dp,np,dp | complete | 120 | 120 | 110 | 120 | 2015-04-25 | 2015-04-27
2 | US10 | Notification bar | ns | complete | 60 | 60 | 50 | 60 | 2015-04-27 | 2015-04-28
2 | US11 | Google Maps | dp,np,dp | complete | 80 | 180 | 50 | 50 | 2015-04-29 | 2015-04-29
| Future | Online Payment |  |  | 300 | 180
| Future | Text Notification

## User Stories
Story ID | Story Name | Story Description | Est Size | Est Time | Class File Names
US01 | Site Skeleton | A basic interface framework | 50 | 120 | style.css
US02 | Home Page | The Home page is where the right side pane will have a log in and the left hand pane will have basic info about the system | 30 | 120 | home.jsp
US03 | Log In Pane | The Log In Pane is where the user or admin will log in to check/update the status | 30 | 60 | home.jsp
US04 | Registration Page | The Registration Page is where the user or admin can register for a login | 40 | 90 | registration.jsp
US05 | About Us Page | The About Us page is where the information about the team and the website will be | 30 | 60 | aboutus.jsp
US06 | Website Design (Uniform) | The uniform design layout through all pages | 60 | 240 | style.css
US07 | Contact Us (Feedback) Page | The contact us page will show the the infromation about the creaters of the website as well as about the laundry management owners | 80 | 60 | contactus.jsp
US08 | FAQs page | This page contains some basic login problem information and password reset information | 50 | 90 | home.jsp
US09 | Status Page | This page shows the current status of laundry managed by the owner of the laundrament | 90 | 120 | status.jsp
US10 | Notification bar | This page sends the email notification of confirming the laundry status | 60 | 60 | status.jsp
US11 | Google Maps | This page allows user to locate business easily | 60 | 250 | map.jsp

## Tests
AT ID | Story ID | Story Name | Input | Expected Output
AT01 | US01 | Site Skeleton | Visual display | Expected visual display
AT02 | US02 | Home Page | Click on home button | Lead you to the home page
AT03 | US03 | Log In Pane | Click on log in button | Lead you to the log in page
AT04 | US04 | Registration Page | Click on registration button | Lead you to the registration page
AT05 | US05 | About Us Page | Click on about us button | Lead you to the about us page
AT06 | US06 | Website Design (Uniform) | Desging the template | Expected display
AT07 | US07 | Contact Us (Feedback) Page | Click on contact us button | Lead you to the contact us page
AT08 | US08 | FAQs page | Click on FAQs | Lead you to the FAQs page
AT09 | US09 | Status Page | Update/Remove Records | Updates the status
AT10 | US10 | Notification bar | Once the status is updated | Email will be sent of the status
AT11 | US11 | Google Maps | Click on maps | Will lead you to google maps/satellite

## Burndown
Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
2015-04-02 | 12 |  | 0
2015-04-16 | 7 | 4 | 250 | 200 | 75 | Red = Accomplished
2015-04-30 | 0 | 7 | 500 | 250 | 60 | Green = Estimated

## Sprint 1
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US01 | Site Skeleton | AT01 | dp,st,dp,ss,kp,np,ns,ak | Done | 120 | 60 | 100 | 90 | 2015-04-16
T01.01 | Visual display - Expected visual display
US02 | Home Page | AT02 | dp,np,ak,ss,st | Done | 100 | 120 | 120 | 100 | 2015-04-16
T02.01 | Click on home button - Lead you to the home page
US 03 | Log In Pane/Log out | AT03 | dp,np | Done | 90 | 120 | 120 | 60 | 2015-04-16
T03.01 | Click on log in button - Lead you to the log in page |  | ak
US 04 | Registration Page | AT04 | dp,dp,np | Done | 120 | 150 | 60 | 90 | 2015-04-16
T04.01 | Click on registration button - Lead you to the registration page
Review Results
All Userstories in Sprint 1 tested and check for success and failure. The testing results work as per requirement.
Keep doing:
Meet twice a week
Text everyone when you discover a problem
Avoid:
Not updating GitHub
Scheduling meeting on Thursday

## Sprint 2
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US01 | About Us Page | AT01 | dp,st,ns,ss,ak,kp | Done | 120 | 60 | 100 | 90 | 2015-04-30
T01.01 | Visual display - Expected visual display
US02 | Website Design (Uniform) | AT02 | st,ss,kp,ak | Done | 100 | 120 | 120 | 100 | 2015-04-30
T02.01 | Visual display - Expected visual display
US 03 | Contact Us (Feedback) Page | AT03 | st,dp,ns,ss | Done | 90 | 120 | 120 | 60 | 2015-04-30
T03.01 | Lead you to the contact us page
US 04 | FAQs page | AT04 | dp,ns,kp,ak | Done | 120 | 150 | 60 | 90 | 2015-04-30
T04.01 | Lead you to the FAQs page
US 05 | Status Page | AT05 | dp,np | Done | 120 | 90 | 100 | 60 | 2015-04-30
T05.01 | Click on log in button-Lead you to the log in status
US 06 | Notification bar | AT06 | dp | Done | 90 | 150 | 120 | 60 | 2015-04-30
T06.01 | Email will be sent of the status
US 07 | Google Maps | AT07 | dp,np | Done | 120 | 120 | 150 | 60
T07.01 | Will lead you to google maps/satellite
Meet twice a week
Text everyone when you discover a problem
Avoid:
Not updating GitHub
Scheduling meeting on Thursday